Project Breakdown: School Management System

Phase 1: Project Planning & Architecture (Week 1)

Goal: Set up foundation and planning

Tasks:

- Requirements Finalization (2 days)

  - Confirm all user roles (Admin, Teacher, Student)

  - Define exact features for each role

  - Finalize report formats and printing requirements

- Database Schema Design (2 days)

  - Finalize all tables (you have good start)

  - Add missing tables: attendance, fees payments, notifications

  - Define all relationships and constraints

- Project Structure Setup (1 day)

  - Create organized folder structure

  - Set up version control (Git)

  - Configure development environment

Phase 2: Core System Development (Weeks 2-3)

Goal: Build foundational modules

Tasks:

- User Authentication & Authorization (3 days)

  - Login/Logout system

  - Role-based access control

  - Password reset functionality

  - Session management

- Admin Dashboard (4 days)

  - Student registration module

  - Teacher registration module

  - Class/Form management

  - Subject allocation

  - User management

- Student Management Module (3 days)

  - Student profile management

  - Class assignment

  - Student search/filter

  - Bulk operations

Phase 3: Academic Modules (Weeks 4-5)

Goal: Implement core academic features

Tasks:

- Teacher Portal (4 days)

  - Dashboard for teachers

  - Class/subject assignment

  - Student list viewing

  - Basic profile management

- Exam Results Management (5 days)

  - Midterm results entry interface

  - End-of-term results entry

  - Results validation

  - Automatic grade calculation

  - Class ranking system

- Report Generation System (4 days)

  - Individual student reports

  - Class ranking reports

  - Term progress reports

  - Print functionality (HTML/PDF)

Phase 4: Advanced Features (Week 6)

Goal: Add value-added features

Tasks:

- Attendance Tracking (3 days)

  - Daily attendance marking

  - Attendance reports

  - Absence notifications

- Fees Management (3 days)

  - Fees structure setup

  - Payment recording

  - Balance tracking

  - Payment receipts

- Communication Module (2 days)

  - Announcements system

  - Notifications

  - Basic messaging

Phase 5: Testing & Deployment (Week 7)

Goal: Ensure stability and go live

Tasks:

- System Testing (3 days)

  - Unit testing

  - Integration testing

  - User acceptance testing

  - Security testing

- Performance Optimization (2 days)

  - Database optimization

  - Code optimization

  - Caching implementation

- Deployment & Documentation (2 days)

  - Server setup

  - Deployment

  - User documentation

  - Admin manual